## Intake Log
THERAGEN — Integrated Intake Log
Document ID: THG-ENT-INT-LOG · Version 1.0 · Baseline · Companion to Intake Form THG-ENT-INT-001
Intake ID | Date submitted | Date triaged | Requester | Department | Request title | Request type | Primary dept (assigned) | Secondary depts | Compliance flags | PHI? | 21 CFR Part 11? | Clinical? | Effort | Budget envelope | Decision | Project ID | Charter Doc ID | Days to triage (calc) | Status | Triaged by | Notes
INT-2026-0001 | 2026-05-04 | 2026-05-05 | Dr. M. Patel | Clinical / Medical Affairs | Cardio device feasibility study | Clinical or study request | Clinical / Medical Affairs | Regulatory, R&D, IT | 21 CFR Part 11; HIPAA | Y | Y | Y | Medium | $250k–1M | Approved → Charter | THG-CLN-CHR-014 | THG-CLN-CHR-014 |  | In flight | PMO Triage | Pre-screened with Regulatory.
INT-2026-0002 | 2026-05-11 | 2026-05-12 | L. Okafor | Finance / Procurement | Vendor onboarding — outcomes analytics | Vendor / procurement | Finance / Procurement | IT, Legal | SOC 2 | N | N | N | Small | $25–250k | Approved → Work Order | THG-FIN-WRK-003 | — |  | In flight | PMO Triage | Security review scheduled.
INT-2026-0003 | 2026-05-18 | 2026-05-19 | S. Chen | IT / Data / Security | EDC change — eCRF v3.2 | System change | IT / Data / Security | Clinical, Regulatory | 21 CFR Part 11 | N | Y | Y | Small | $0–25k | Approved → Work Order | THG-IT-WRK-021 | — |  | Complete | PMO Triage | Validation pack attached.

## Dashboard
Intake Dashboard
Live metrics over the Intake Log.
Total submissions | 3
Approved → Charter | 1
Approved → Work Order | 2
Returned | 0
Declined | 0
PHI-flagged | 1
21 CFR Part 11-flagged | 2
Clinical-flagged | 2
Avg days to triage | —
Max days to triage | 0