## README
THERAGEN — Cross-Department RACI Matrix
Document ID: THG-ENT-RAC-001 · Version 1.0 · Baseline
Purpose | Single source of truth for which department plays which role on every Theragen artifact and intake-process step. Used together with the Documentation Standards Guide (THG-ENT-STD-001) and the Master Document Index (THG-ENT-IDX-001).
How to read | Each row is an artifact or intake step. Each column is a department. Each cell carries one of:
R | Responsible — does the work. Multiple R per row allowed.
A | Accountable — owns the outcome. EXACTLY ONE A per row.
C | Consulted — two-way input before decision.
I | Informed — one-way notification after decision.
Blank | Department not engaged on this row.
Tailoring | Individual project documents may TIGHTEN this matrix (e.g., elevate a C to R) but may not LOOSEN it (e.g., drop an A or strip a Consulted department). Tailoring is recorded in the document's own RACI footprint.
Review cycle | Annual, or upon major change to the Theragen org chart.
Owner | PMO Director
Approver | Chief Operating Officer

## Artifact RACI
Artifact-level RACI
Each row is one Theragen document. Each column shows that department's role on that document.
Document ID | Lifecycle Phase | Document Title | CLN | REG | RND | OPS | FIN | COM | IT | HR | A-check
|  |  | Clinical / Medical Affairs | Regulatory / Quality | R&D / Engineering | Operations / PMO | Finance / Procurement | Commercial / Marketing | IT / Data / Security | HR / People
THG-ENT-INT-001 | Intake | Integrated Intake Form | C | C | C | A | C | C | C | C | OK
THG-OPS-CHR-001 | Initiating | Project Charter | C | C | C | A | C | C | I | I | OK
THG-OPS-STK-001 | Initiating | Stakeholder Register | C | C | C | A | I | C | I | I | OK
THG-OPS-SCP-001 | Planning | Project Scope Statement | C | C | R | A | I | C | I | I | OK
THG-OPS-WBS-001 | Planning | Work Breakdown Structure | C | C | R | A | C | I | C | I | OK
THG-OPS-WBD-001 | Planning | WBS Dictionary | C | C | R | A | I | I | C | I | OK
THG-OPS-SCH-001 | Planning | Project Schedule | C | C | R | A | C | I | C | I | OK
THG-OPS-BUD-001 | Planning | Cost / Budget Estimate | C | C | C | R | A | I | I | I | OK
THG-OPS-PMP-001 | Planning | Project Management Plan | C | C | C | A | C | C | C | C | OK
THG-OPS-RSK-001 | Planning | Risk Register & Plan | C | R | C | A | C | C | C | C | OK
THG-OPS-COM-001 | Planning | Communications Management Plan | I | I | I | A | I | C | C | I | OK
THG-OPS-QLP-001 | Planning | Quality Management Plan | C | A | C | R | I | I | C | I | OK
THG-OPS-CHG-001 | Executing | Change Log & Change Request | C | C | C | A | C | C | C | I | OK
THG-OPS-STA-001 | Monitoring | Project Status Report | I | I | I | A | I | I | I | I | OK
THG-OPS-LLN-001 | Closing | Lessons Learned & Closure | C | C | C | A | C | C | C | I | OK
THG-ENT-RAC-001 | Governance | Cross-Department RACI Matrix | I | C | I | A | I | I | I | I | OK
THG-ENT-IDX-001 | Governance | Master Document Index | I | I | I | A | I | I | I | I | OK
THG-ENT-STD-001 | Governance | Documentation Standards Guide | I | C | I | A | I | I | C | I | OK
|  | Accountabilities per department → | 0 | 1 | 0 | 16 | 1 | 0 | 0 | 0

## Intake Process RACI
Integrated Intake — Process-step RACI
Each row is one step in the cross-department intake workflow.
# | Intake Step | CLN | REG | RND | OPS | FIN | COM | IT | HR | A-check
|  | Clinical / Medical Affairs | Regulatory / Quality | R&D / Engineering | Operations / PMO | Finance / Procurement | Commercial / Marketing | IT / Data / Security | HR / People
1 | Submit request | R | R | R | R | R | R | R | R | OK
2 | Triage & route | C | C | C | A | I | I | C | I | OK
3 | Assign Intake ID & primary owner | I | I | I | A | I | I | I | I | OK
4 | Compliance pre-screen (PHI / 21 CFR) | C | A | C | R | I | I | R | I | OK
5 | Resource & budget pre-check | I | C | C | A | R | I | C | C | OK
6 | Charter or work-order decision | C | C | C | A | C | C | C | I | OK
7 | Kickoff & artifact creation | C | C | C | A | C | C | C | C | OK
8 | Status reporting cadence | I | I | I | A | I | I | I | I | OK
9 | Change control | C | C | C | A | C | C | C | I | OK
10 | Closure & lessons learned | C | C | C | A | C | C | C | I | OK

## Legend
Legend & Conventions
Code | Role | Meaning
R | Responsible | Does the work. Multiple R per row allowed.
A | Accountable | Owns the outcome. EXACTLY ONE A per row.
C | Consulted | Two-way input before decision.
I | Informed | One-way notification after decision.
| (blank) | Department not engaged on this row.
Department codes used in headers:
Code | Department
CLN | Clinical / Medical Affairs
REG | Regulatory / Quality
RND | R&D / Engineering
OPS | Operations / PMO
FIN | Finance / Procurement
COM | Commercial / Marketing
IT | IT / Data / Security
HR | HR / People