THG-ENT-SOP-003  ·  Executing & Controlling  ·  Cross-Functional

Standard Operating Procedure — Change Control

Defines how changes to baselined scope, schedule, cost, quality, or controlled documents are requested, assessed, approved, implemented, and verified.

# A.  Document Control

| Document ID | THG-ENT-SOP-003 |
| --- | --- |
| Version | 1.0 |
| Status | BASELINE |
| Effective Date | YYYY-MM-DD |
| Document Owner | PMO Director |
| Approver / Signatory | Chief Operating Officer |
| Review Cycle | Annual |
| Classification | Confidential – Internal |

# B.  Intake Linkage

Links this document to the originating cross-departmental request. Maintains traceability from intake to closure.

| Intake ID | «auto-assigned at intake» |
| --- | --- |
| Originating Request | «linked Intake Form ID» |
| Triggering Department | Operations / PMO |
| Lifecycle Phase | Executing |
| Linked Charter / Workstream | «Project / Program / Workstream reference» |

# C.  Cross-Functional RACI Footprint

How each department engages with this document. R = Responsible, A = Accountable, C = Consulted, I = Informed. Leave blank if not engaged.

| Department | Role | Specific Touchpoint |
| --- | --- | --- |
| Clinical / Medical Affairs | C | «activity, decision, or artifact» |
| Regulatory / Quality | C | «activity, decision, or artifact» |
| R&D / Engineering | C | «activity, decision, or artifact» |
| Operations / PMO | A | «activity, decision, or artifact» |
| Finance / Procurement | C | «activity, decision, or artifact» |
| Commercial / Marketing | C | «activity, decision, or artifact» |
| IT / Data / Security | C | «activity, decision, or artifact» |
| HR / People | I | «activity, decision, or artifact» |

# D.  Compliance & Traceability

Regulatory and methodological frames that govern this artifact. Cite specific clauses where they apply.

| Frame | Applies To | Evidence / Reference |
| --- | --- | --- |
| FDA 21 CFR Part 11 | «which sections of this doc» | «audit evidence, SOP, link» |
| HIPAA | «which sections of this doc» | «audit evidence, SOP, link» |
| PMBOK 7th Ed. | «which sections of this doc» | «audit evidence, SOP, link» |

# 1.  Purpose

To ensure no baselined scope, schedule, cost, quality criterion, or controlled document is changed without documented impact assessment, the right level of approval, verified implementation, and updates to every dependent artifact.

# 2.  Scope

## In scope

Any change to a baselined PMBOK artifact (charter, scope, schedule, budget, quality criteria).

Any revision to a controlled document under SOP-001 beyond Class A (minor).

Changes to validated systems or to PHI handling that affect a baselined record.

## Out of scope

Changes to drafts that have not yet been baselined.

Operational corrections within an approved tolerance band defined in the PM Plan.

# 3.  Definitions

| Term | Definition |
| --- | --- |
| Change Request (CR) | Form proposing a change; one per change. Identifier C-NNN. |
| Class A change | Minor — no impact on meaning, controls, or scope. |
| Class B change | Substantive — wording or process change without compliance impact. |
| Class C change | Controlling — change to controls, scope, or compliance frame. |
| Verification | Confirmation that the implemented change behaves as approved. |
| Linked artifacts | All documents and registers updated to reflect the approved change. |

# 4.  Roles & Responsibilities

These role assignments are binding under this SOP. They tighten — never loosen — the enterprise baseline in THG-ENT-RAC-001.

| Role | Responsibility under this SOP |
| --- | --- |
| Requester | Submits the Change Request with rationale and initial impact estimate. |
| Project Manager | Logs and classifies; coordinates impact assessment. |
| Impact Assessors | Each affected department's lead provides scope/schedule/cost/quality impact. |
| Change Approver | Approves, rejects, or defers per the Approval Matrix. |
| Implementer | Executes the approved change and reports verification. |
| Quality / Regulatory | Confirms compliance impact assessment for Class C changes. |

# 5.  Procedure

The procedure below is mandatory. Deviations require a documented justification and follow §9 (Deviations & CAPA).

## 5.1  Submit Change Request

Performed by:  Requester

Open a Change Request on the Change Log template (THG-OPS-CHG-NNN).

Reference the Intake ID and the baselined artifacts affected.

State the change, the reason, and the impact if not approved.

Evidence recorded:  CR row created in Change Log; status = PENDING.

## 5.2  Log & classify

Performed by:  Project Manager

Assign Change ID (C-NNN).

Classify A / B / C using the Approval Matrix.

Evidence recorded:  Class recorded in Change Log.

## 5.3  Impact assessment

Performed by:  Impact Assessors (affected departments)

Each affected department lead returns scope / schedule / cost / quality impact within 5 business days.

Quality / Regulatory provides a compliance impact statement for Class C.

Evidence recorded:  Impact statements attached to the CR record.

## 5.4  Approval decision

Performed by:  Change Approver

Approve, reject, or defer with documented rationale.

Class C approvals require Quality / Regulatory co-signature.

Evidence recorded:  Decision recorded in Change Log with Approver name and date.

## 5.5  Implement

Performed by:  Implementer

Execute the approved change.

Update every linked artifact (versions incremented per SOP-001).

Evidence recorded:  Updated artifacts published; Master Index reflects new versions.

## 5.6  Verify

Performed by:  Project Manager

Confirm the implemented change matches the approved description.

Confirm all linked artifacts are updated.

Evidence recorded:  Verification attestation in Change Log.

## 5.7  Close

Performed by:  Project Manager

Update Change Log status to CLOSED.

Notify stakeholders per the Communications Plan.

Evidence recorded:  Change Log CLOSED; notification archived.

# 6.  Process Flowchart

Figure 1.  Change request to verified implementation across affected departments.

# 7.  Decision Authority / Approval Matrix

| Decision class | Threshold / criteria | Approval authority | Records location |
| --- | --- | --- | --- |
| Class A — minor | No impact on meaning, controls, or scope | Document Owner | Doc Z-3 |
| Class B — substantive | No compliance impact; ≤10% schedule or budget | Project Manager + Sponsor | Change Log |
| Class C — controlling | Compliance impact OR >10% schedule/budget OR scope change | Sponsor + Quality / Regulatory | Change Log + eQMS |
| Emergency / Safety | Patient or regulatory exposure | Quality Director (notify within 24h) | eQMS |

# 8.  KPIs & Monitoring

Process owner reports the following KPIs to the Quality Council on the stated cadence.

| KPI | Target | Method | Cadence | Owner |
| --- | --- | --- | --- | --- |
| Impact assessment SLA | ≤5 business days | Change Log | Per CR | PMO Director |
| CR cycle time (open→close) | ≤15 business days | Change Log | Monthly | PMO Director |
| CRs implemented without verification | 0 | Audit spot-check | Quarterly | Quality |
| Linked-artifact update completeness | 100% | Audit spot-check | Quarterly | Quality |

# 9.  Deviations, Nonconformities & CAPA

Any deviation from this procedure shall be documented at the time of occurrence. The Document Owner evaluates each deviation for severity and may open a Corrective and Preventive Action (CAPA) record in the eQMS. Repeat deviations require root-cause analysis and SOP revision.

| Severity | Definition | Required action | Owner |
| --- | --- | --- | --- |
| Minor | Isolated, no impact on record integrity or compliance | Log in deviation log; corrective action by next review | Document Owner |
| Major | Impact on record integrity, traceability, or stakeholder trust | Open CAPA; root-cause within 14 days | Quality Lead |
| Critical | Impact on regulatory submission, patient safety, or audit findings | Open CAPA immediately; notify Sponsor and Regulatory within 24 hours | Quality / Regulatory Director |

# 10.  Training Requirements

Personnel performing work under this SOP shall complete the training listed below before performing controlled activities, and again whenever a major revision is issued.

| Audience | Training content | Comprehension check | Refresh cadence | Evidence |
| --- | --- | --- | --- | --- |
| Project Managers, Change Approvers, Department Leads serving as Impact Assessors | Read this SOP; review the linked Standards Guide block where referenced | Short comprehension quiz (≥80% pass) | Annual or upon major revision | HR / Compliance training records |

# 11.  References & Related Documents

| Reference | Relationship |
| --- | --- |
| THG-OPS-CHG-NNN — Change Log & Change Request | The instrument this SOP operates on. |
| SOP-001 — Document Control | Governs version updates after change. |
| SOP-004 — Records Management | Governs retention of CR records. |
| 21 CFR Part 11 §11.10(e), §11.10(k) | Audit trail and access controls. |
| ISO 13485 §7.3.9 | Control of design changes. |

# 12.  Records & Retention

| Record | System of record | Retention | Disposition |
| --- | --- | --- | --- |
| Change Requests (open + closed) | Change Log + eQMS for Class C | 7 years | Archive |
| Impact assessments | Change Log attachments | 7 years | Archive |
| Verification attestations | Change Log | 7 years | Archive |

# Z-1.  Handoffs & Downstream Artifacts

Predecessors and successors in the integrated document lifecycle.

## Receives input from

Project Management Plan, Baselined artifacts being changed

Intake Log linkage

## Feeds into

Updated linked artifacts; Status Reports; Lessons Learned.

# Z-2.  Approval Signatures

| Role | Name | Signature | Date |
| --- | --- | --- | --- |
| Chief Operating Officer |  |  |  |
| PMO Director |  |  |  |
| Quality / Regulatory Director |  |  |  |

# Z-3.  Revision History

| Version | Date | Author | Summary of Change | Approved By |
| --- | --- | --- | --- | --- |
| 0.1 | YYYY-MM-DD | «author» | Initial draft |  |
| 1.0 | YYYY-MM-DD | «author» | Approved baseline |  |